## OKRs_Timeline
Strategy | Objective | Key Result (KR) | Start Date | End Date
Robust TCoE Ecosystem | Identify and Engage Key Stakeholders | Develop list of key stakeholder teams | 2025-01-01 | 2025-01-15
Robust TCoE Ecosystem | Identify and Engage Key Stakeholders | Identify lead contacts within each group | 2025-01-01 | 2025-01-15
Robust TCoE Ecosystem | Identify and Engage Key Stakeholders | Capture and prioritize objectives | 2025-01-15 | 2025-02-15
Robust TCoE Ecosystem | Assess the Current TCoE Ecosystem | Document existing methodologies | 2025-01-01 | 2025-01-31
Robust TCoE Ecosystem | Assess the Current TCoE Ecosystem | Conduct SWOT analysis | 2025-02-01 | 2025-02-15
Robust TCoE Ecosystem | Assess the Current TCoE Ecosystem | Collect structured feedback | 2025-02-15 | 2025-03-15
Robust TCoE Ecosystem | Design an Enhanced TCoE Operating Model | Compile inventory of tools | 2025-01-15 | 2025-02-15
Robust TCoE Ecosystem | Design an Enhanced TCoE Operating Model | Develop preliminary TOM draft | 2025-02-15 | 2025-03-15
Robust TCoE Ecosystem | Design an Enhanced TCoE Operating Model | Present and discuss TOM | 2025-03-15 | 2025-04-15
Robust TCoE Ecosystem | Design an Enhanced TCoE Operating Model | Design communication plan | 2025-04-15 | 2025-05-15
Robust TCoE Ecosystem | Build a High-Performing TCoE Team | Define org structure | 2025-01-15 | 2025-02-15
Robust TCoE Ecosystem | Build a High-Performing TCoE Team | Identify and hire key roles | 2025-02-15 | 2025-06-15
TCoE as R&D Lab | Build a High-Performing TCoE Team | Develop contingency plan | 2025-06-15 | 2025-07-15
TCoE as R&D Lab | Establish Automated Global Test Packages | Identify core test packages | 2025-01-15 | 2025-02-15
TCoE as R&D Lab | Establish Automated Global Test Packages | Develop high-level test cases | 2025-02-15 | 2025-04-15
TCoE as R&D Lab | Establish Automated Global Test Packages | Conduct stakeholder reviews | 2025-04-15 | 2025-05-15
TCoE as R&D Lab | Establish Automated Global Test Packages | Automate test packages | 2025-05-15 | 2025-07-15
TCoE as R&D Lab | Implement Centralized Test Script Management | Create repository for test scripts | 2025-01-15 | 2025-02-15
TCoE as R&D Lab | Implement Centralized Test Script Management | Organize scripts by category | 2025-02-15 | 2025-03-15
TCoE as R&D Lab | Implement Centralized Test Script Management | Implement onboarding framework | 2025-03-15 | 2025-04-15
Trusted Partnership | Foster a Pipeline of Proof of Concepts (PoCs) | Solicit PoC suggestions | 2025-02-15 | 2025-03-15
Trusted Partnership | Foster a Pipeline of Proof of Concepts (PoCs) | Evaluate and categorize PoCs | 2025-03-15 | 2025-04-15
Trusted Partnership | Foster a Pipeline of Proof of Concepts (PoCs) | Integrate PoCs into Global Packages | 2025-04-15 | 2025-05-15
Trusted Partnership | Foster a Pipeline of Proof of Concepts (PoCs) | Develop specialized test packages | 2025-05-15 | 2025-07-15
Trusted Partnership | Introduce and Establish TCoE with Stakeholders | Conduct introductory meetings | 2025-01-15 | 2025-01-31
Trusted Partnership | Introduce and Establish TCoE with Stakeholders | Set up regular engagements | 2025-01-31 | 2025-06-30
Trusted Partnership | Introduce and Establish TCoE with Stakeholders | Document expectations | 2025-02-15 | 2025-03-15
Trusted Partnership | Align Sub-Value Streams with Stakeholder Needs | Identify services and capabilities | 2025-01-15 | 2025-02-15
Aspire Toward a Future-Ready TCoE | Align Sub-Value Streams with Stakeholder Needs | Appoint SVS leads | 2025-02-15 | 2025-03-15
Aspire Toward a Future-Ready TCoE | Align Sub-Value Streams with Stakeholder Needs | Develop SVS-specific OKRs | 2025-03-15 | 2025-04-15
Aspire Toward a Future-Ready TCoE | Establish Contingency Plans for Critical Scenarios | Identify conflicts | 2025-02-15 | 2025-03-15
Aspire Toward a Future-Ready TCoE | Establish Contingency Plans for Critical Scenarios | Prioritize critical requirements | 2025-03-15 | 2025-04-15
Aspire Toward a Future-Ready TCoE | Establish Contingency Plans for Critical Scenarios | Develop essential test case list | 2025-04-15 | 2025-05-15
Aspire Toward a Future-Ready TCoE | Deliver Effective User Training and Support | Establish support channels | 2025-03-15 | 2025-04-15
Aspire Toward a Future-Ready TCoE | Deliver Effective User Training and Support | Create training resources | 2025-04-15 | 2025-05-15
Aspire Toward a Future-Ready TCoE | Deliver Effective User Training and Support | Develop continuous support model | 2025-05-15 | 2025-06-15
Aspire Toward a Future-Ready TCoE | Identify and Address Current Weaknesses | List known data quality issues | 2025-01-15 | 2025-02-15
Aspire Toward a Future-Ready TCoE | Identify and Address Current Weaknesses | Map projects to data quality issues | 2025-02-15 | 2025-03-15
Aspire Toward a Future-Ready TCoE | Identify and Address Current Weaknesses | Develop data quality roadmap | 2025-03-15 | 2025-04-15
Aspire Toward a Future-Ready TCoE | Define and Plan Future State Architecture | Gather stakeholder insights | 2025-02-15 | 2025-03-15
Trusted Partnership | Define and Plan Future State Architecture | Identify limitations | 2025-03-15 | 2025-04-15
Trusted Partnership | Define and Plan Future State Architecture | Outline future state action steps | 2025-04-15 | 2025-05-15